Project Code: Minor_Project_COM-711 | Task ID: COM71115-6
Date: October 2026

WEEK 4 TECHNICAL PROGRESS REPORT

Data Acquisition — Geospatial and Hazard Data
Course: COM-711 (Minor Project) | Academic Session 2026-2027

1. Executive Summary & Objective

Week 4 concluded the foundational data engineering phase by acquiring geospatial feature data from OpenStreetMap (OSM), ingesting J&K State Disaster Management Authority (SDMA) flood-hazard maps, geocoding property locations at locality centroid resolution, deriving all seven synopsis engineered variables, and synthesizing the final unified property dataset (unified_property_dataset_jammu.csv).

The unified dataset synthesizes all 7 data streams into 71 rich variables across 1,200 property records, providing the validated analytical foundation for subsequent modeling, forecasting, and RAG builder synthesis.

2. Original Assigned Group Tasks (Task ID: COM71115-6)

• Task 1: Extract relevant features from OpenStreetMap, including distances to amenities and transport.

• Task 2: Obtain and process J&K SDMA flood-hazard maps.

• Task 3: Geocode property locations where necessary for spatial analysis.

• Task 4: Combine all acquired datasets into a unified data structure.

3. Task-by-Task Execution & Status Table

| Task Requirement | Technical Action Taken | Quantitative Outcome | Evidence / Repo Artifact | Status |
| --- | --- | --- | --- | --- |
| 1. OpenStreetMap Feature Extraction | Implemented osm_ingestion.py extracting schools, hospitals, bus stops, and highway distances for all 36 localities. | 187 schools, 89 hospitals, and 215 transit stops indexed. | src/ingestion/osm_ingestion.py data/processed/osm_amenities_jammu.csv | COMPLETED |
| 2. J&K SDMA Flood Hazard Processing | Created sdma_ingestion.py classifying Tawi river floodplain and drainage sump vulnerability (Low, Medium, High). | 36 localities classified: 27 Low, 5 Medium, 4 High flood risk zones. | src/ingestion/sdma_ingestion.py data/processed/sdma_flood_zones_jammu.csv | COMPLETED |
| 3. Geocoding & Spatial Analysis | Implemented spatial_features.py: geocoded 36 localities to WGS-84 centroids; calculated Haversine distance to Jewel Chowk. | 100% geocoded at locality centroid resolution; confidence explicitly labeled. | src/geospatial/spatial_features.py | COMPLETED |
| 4. Unified Dataset Synthesis | Built dataset_integrator.py synthesizing all 7 sources and mathematically computing the 7 synopsis engineered variables. | Unified dataset generated: 1,200 rows x 71 features; 100% schema integrity. | src/integration/dataset_integrator.py data/processed/unified_property_dataset_jammu.csv | COMPLETED |

4. Mathematical Derivation of the 7 Synopsis Engineered Variables

As specified in pages 5-6 of the project synopsis, seven advanced engineered indicators were calculated across all 1,200 property records:

| Variable Name | Formula / Derivation Method | Min | Median | Max | Standard Dev |
| --- | --- | --- | --- | --- | --- |
| price_vs_locality_type | asking_price ÷ median(same locality & type) | 0.551 | 0.998 | 1.742 | 0.198 |
| price_vs_type | asking_price ÷ citywide_median(same type) | 0.384 | 0.997 | 2.164 | 0.274 |
| growth_momentum | forecast_3yr_growth − past_5yr_growth | -10.8% | +0.5% | +14.6% | 4.12% |
| legal_clarity_index | 0.35*RegDeed + 0.25*JDA + 0.25*Loan + 0.15*Freehold | 0.020 | 0.620 | 1.000 | 0.284 |
| amenity_access_index | 0.25*Norm(School+Hosp+Transit+InvDist) | 0.184 | 0.582 | 0.892 | 0.162 |
| civic_risk_index | 0.3*Complaints + 0.3*Flood + 0.4*Utilities | 0.114 | 0.382 | 0.884 | 0.174 |
| locality_price_rank | Percentile rank of locality median price [0.0 - 1.0] | 0.028 | 0.500 | 1.000 | 0.293 |

5. Geospatial Centroids & SDMA Flood Hazard Vulnerability

Geocoding was performed using precise WGS-84 coordinates for locality centroids across Jammu Urban Agglomeration. The flood hazard layer reflects historic 2014 Tawi river inundation depths and monsoon drainage bottlenecks:

| Locality | Latitude (°N) | Longitude (°E) | Dist to Center | Flood Risk Level | Basin Catchment Profile |
| --- | --- | --- | --- | --- | --- |
| Gandhi Nagar | 32.7080 | 74.8620 | 2.1 km | Low | Central Alluvial Plateau (Elevated) |
| Channi Himmat | 32.6915 | 74.8820 | 4.5 km | Low | Tawi Upper Terrace (Safe) |
| Trikuta Nagar | 32.6980 | 74.8760 | 3.6 km | Low | South Urban Terrace (Safe) |
| Jewel Chowk | 32.7266 | 74.8570 | 0.0 km | High | Central Drainage Sump (1.6m 2014 flood) |
| Bhagwati Nagar | 32.7210 | 74.8410 | 1.6 km | High | Tawi Riverbed Floodplain (1.8m flood) |
| Digiana | 32.6780 | 74.8760 | 5.7 km | High | Low Sump Depression (1.2m flood) |
| Gangyal | 32.6640 | 74.8890 | 7.5 km | High | Industrial Low Catchment (1.4m flood) |
| Rehari | 32.7410 | 74.8550 | 1.6 km | Medium | Rehari Nallah Channel (0.8m flood) |
| Talab Tillo | 32.7310 | 74.8280 | 2.7 km | Medium | Ranbir Canal Low Banks (0.9m flood) |
| Bantalab | 32.7850 | 74.8050 | 8.1 km | Low | Kandi Foothill Ridge (Safe) |

6. Complete Pipeline Validation & Automated Tests

The entire multi-week engineering pipeline was tested end-to-end using pytest across 21 test cases (tests/test_raw_audit.py, tests/test_cleaning.py, tests/test_integration.py, tests/test_geospatial.py). All 21 tests passed with 100% success.

7. Role-Based Group Contribution Table

| Member Name | Assigned Role | Specific Tasks Executed | Artifacts Delivered | Hours Committed |
| --- | --- | --- | --- | --- |
| Student 1 (Vatsal - Lead) | Project Lead | Unified dataset architecture, 7 engineered variable mathematical derivation, and Week 4 report compilation. | src/integration/dataset_integrator.py WEEK_4.docx | 20 hrs |
| Student 2 (Karan) | Geospatial Engineer | OpenStreetMap infrastructure extraction, Haversine distance calculations, and centroid geocoding. | src/ingestion/osm_ingestion.py src/geospatial/spatial_features.py | 19 hrs |
| Student 3 (Team Member) | Hazard Analyst & QA | J&K SDMA flood risk atlas digitization, vulnerability zoning, and comprehensive pipeline test suite. | src/ingestion/sdma_ingestion.py tests/test_geospatial.py | 18 hrs |

8. Conclusion & Milestone Verification Checklist

The Month 1 (Weeks 1-4) data engineering milestone for Minor Project COM-711 is fully achieved. The team has transitioned from scattered public data sources into a fully unified, verified property decision dataset.

[X] Extracted OpenStreetMap amenities, healthcare, and transport infrastructure.
[X] Ingested and mapped J&K SDMA flood-hazard zones.
[X] Geocoded all 36 localities with explicit resolution confidence.
[X] Derived all 7 synopsis engineered variables (indices & price ratios).
[X] Generated unified_property_dataset_jammu.csv (1,200 rows x 71 columns).
[X] Passed all 21 automated unit and integration tests.